## Time Sheet
Backend Development | Expected Time | Time Spent | Frontend Development | Expected Time | Time Spent | Frontend Design | Expected Time | Time Spent | Graphics | Expected Time | Time Spent | QA | Expected Time | Time Spent
Plugin installation and DB features | 8 | 10 | Products Page | 16 | 24 | Products Page | 16 | 20 | Canvas Graphics | 40 | 120 | All Modules QA | 72 | 120
Order History | 24 | 24 | Category page | 0 | 8 | Category page | 0 | 6 | Configuration menu Graphics | 20 | 32
User Custom Fields | 48 | 40 | Cart Page | 0 | 16 | Cart Page | 0 | 6 |  | 60 | 152
Order Management | 8 | 6 | Checkout Page | 0 | 8 | Checkout Page | 0 | 4
Products Custom Fields | 60 | 68 | Register Page | 28 | 32 | Register Page | 0 | 4
Groups | 40 | 48 | Login Page | 8 | 8 | Login Page | 0 | 4
Configurations | 56 | 64 | Orders Page | 32 | 28 | Orders Page | 0 | 4
Configuration Conditions | 40 | 96 | Accounts Page | 72 | 60 | Accounts Page | 0 | 6
Canvas settings | 12 | 16 | Configuration Menu | 80 | 80 | Configuration Menu | 76 | 84
Taxonomy Order | 16 | 16 | Configuration Canvas | 120 | 110 | Configuration Canvas | 100 | 80
Configuration/Groups/Condtions adding | 40 | 88 | Part number Search Option | 40 | 36 | Part number Search Option result | 8 | 8
Import/Export functions | 56 | 56 | Order Search option | 40 | 36 | Order Search option result | 8 | 4
Punchout API | 80 | 40 | Reorder product | 24 | 24 | Reorder product Page | 4 | 4
| 488 | 572 | Header Menu items | 0 | 4 |  | 212 | 234
|  |  |  | 460 | 474
|  |  | Total Expected | 1292
|  |  | Total Spent | 1552

## Pending-InProgress Worksheet
Task Name | Expected Time
Data Entry for updated Graphics and Configurations | 16
Test and live API updates on Punchout API | 12
28